## Sheet1
| Team: | 8H | Unit: | 2 hrs/day
| Team members: | Hannes Þór Sveinbjörnsson (hths17@hi.is)
Ragnheiður Ásta Karlsdóttir (rak4@hi.is)
Viktor Alex Brynjarsson (vab18@hi.is)
Sprint | User Story ID | User Story | Estimated Team Effort | Priority | Actual Team Effort | Done?
1 | 1 | As a user, I want to find a hotel by name so that I could book a room in that hotel. | 2 | 10
1 | 15 | As a user, I want to book rooms (one or more) in a specific hotel for a certain number of nights at a certain date so that I know I have a booked room(s) when I arrive. | 3 | 10
1 | 21 | Set up database | 2 | 10
1 | 22 | Set up eclipse project + db connection | 1 | 10
1 | 23 | Domain model | 4 | 10
1 | 24 | Design model | 4 | 10
1 | 2 | As a user, I want to find hotel rooms by location so that my search results all fit my geographical needs. | 1 | 20
1 | 3 | As a user, I want to find hotel rooms which are available to me for booking so that I know the search results are available at the time I will need a room. | 1 | 20
1 | 9 | As a user, I want to see details of the types of rooms in a specific hotel so that I know that the rooms available fit my needs. | 2 | 20
2 | 10 | As a user, I want to be able to see the room types and how many are available in a specific hotel so that I know that I can book the rooms I require. | 2 | 20
2 | 12 | As a user, I want to see images of the hotel rooms and the hotel so that I can be assured of it's quality and that it fits my needs. | 5 | 20
2 | 4 | As a user, I want to filter my search results by price so that I can find a hotel room in my price range. | 1 | 30
2 | 5 | As a user, I want to filter my search results by hotel rating so that I can find a hotel room which is up to standard. | 1 | 30
2 | 6 | As a user, I want to filter my search results by the number of beds so that I can find a room with adequate accommodation. | 0.5 | 30
2 | 7 | As a user, I want to filter my search results by the type of bed so that I can find a room with the bed of my preference. | 0.5 | 30
2 | 8 | As a user, I want to filter my search results by amenities (WIFI, breakfast included, 24/7 reception, room service, etc.) so that so that the search results will reflect my needs. | 0.5 | 30
2 | 11 | As a user, I want to see the location of the hotel on a map so that I can verify that it is in the location I am satisfied with. | 8 | 30
| 13 | As a user, I want to see reviews and ratings of the hotel by other guests so that I can be asassured of it's quality and that it fits my needs. | 4 | 30
| 17 | As a hotel director I want to change the location information of my hotel so that the customer get correct information. | 2 | 40
| 18 | As a hotel director I want to be able to add new room types and specify how many rooms of that type are available so that I can enable booking of new rooms. | 3 | 40
| 19 | As a hotel director I want to see the profitability of the rooms in my hotel so I can know whether I need to change any of my rooms' types (eg. twin bed into single bed). | 2 | 40
| 25 | Hotel Director login | 13 | 40
| 14 | As a user, I want to see the interest in a hotel (5 people have viewed this hotel in the last hour, only 4 rooms available at this time) so that I am more likely to book. | 5 | 50
| 16 | As a user, I want to be able to pay for my stay in advance so that I don't have to worry when I get there. | 20 | 50
| 20 | As a marketing executive I want to be able to see a heat map of interest in hotel rooms on top of a map of a city so that I can see where to open new businesses aimed at tourists. | 100 | 50